Weekly Work Plan and Progress Log

CSE498R Directed Research, Department of Electrical and Computer Engineering, North South University

Fahima Shameem, Farjana Rahman Samia

# Week 1 (August 7 to August 10)

Settled on the research question for the semester: whether a commonly used prompt injection filter actually holds up against attackers who put in some effort, not just simple copy paste attempts. Went through recent papers on prompt injection and adaptive attacks to see what had already been tried and where the gaps were. Set up the working environment on Kaggle with Qwen2.5-7B-Instruct as the assistant being tested and ProtectAI's DeBERTa based classifier as the first security filter. Ran a very small first pass just to confirm the pipeline could actually generate responses and get a defense decision back.

# Week 2 (August 11 to August 17)

The first way of checking whether an attack worked was just looking for certain keywords in the response, and it quickly became clear this was unreliable since normal answers used the same words. Switched to using a second language model as a judge that reads the response and decides whether the assistant actually got tricked or not. Added a separate check for whether the response still made sense as a real answer, since a filter that blocks everything is not actually useful. Brought in a second classifier, deepset's injection detector, to compare against the first one, and put together a set of harmless requests to test whether either filter was blocking normal use by mistake. Increased the number of test cases since the first small batch was too noisy to draw any real conclusion from.

# Week 3 (August 18 to August 23)

Designed the two attack methods that make up the main contribution of the project. The first splits a malicious instruction into pieces and hides them among normal looking text, testing what happens when a filter checks each piece on its own rather than the full picture, which is close to how systems that pull in multiple documents at once actually work. The second uses DSPy to let the model itself search for a rewording that gets past the filter, instead of one person guessing at a clever phrasing. Started the full evaluation run across every combination of filter and attack type. This ran long enough that it had to be split across more than one session, so time was also spent making sure the run could pick back up where it left off instead of starting over each time.

# Week 4 (August 24 to August 26)

Noticed that a small share of the judge's answers were coming back in a format that could not be read automatically, which was quietly being counted as a failed attack by default. Went back and reprocessed those specific cases until nearly all of them had a real answer instead of a guess. Recalculated the statistics with the corrected data and confirmed the results held up. Put together a summary chart of the findings and a small browsable tool so the results could be looked through without needing to read raw numbers. The experimental part of the project was complete as of August 26.

# Remaining Plan

From this point on the work still ahead is writing, not further testing.

## Week 5

Write the methodology and results sections of the paper using the finalized data and charts.

Write the introduction, related work, and discussion sections. Share a full draft with the supervisor for feedback.

## Week 6

Revise the paper based on feedback, tighten the writing, and finalize references and formatting.

Final proofread and submission.